## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Choosing a tablet vendor
Research tablet system options |  |  |  | 2 days
Generate quotes and review costs |  |  |  | 2 days
Test out tablet systems capabilities |  |  |  | 5 days
Choose a tablet system |  |  |  | 2 days
Sign contract with menu tablet vendor |  |  |  | 2 days
Milestone: Tablet delivery
Decide how many tablets are required |  |  |  | 4 hours
Put the order with the vendor |  |  |  | 3 hours
Old tablets shipment |  |  |  | 11 days
New tablets shipment |  |  |  | 4 weeks
Milestone: Tablet installation
Determine the extent of installation at each location in the bar area |  |  |  | 5 hours
Schedule an electrician to wire up the tables |  |  |  | 3 hours
Install tablets in the bar areas at the Downtown and North restaurant locations | - we can’t close the restaurants for a full day we need to schedule two half-days at each location - Notify GMs when their locations need to close for wiring |  |  | 4 days
Milestone: creating the tablet visual content
Choose menu items and coupon values to feature in the tablets |  |  |  | 1 week
Send the content to the designers |  |  |  | 2 hours
Designing of the mock-ups |  |  |  | 4 days
Evaluate the designs |  |  |  | 2 hours
Load the mock-ups on the tablets |  |  |  | 4 hours
Milestone: Tablet integration with existing systems
Establish security measures for data traffic on tablets |  |  |  | 1 day
Integrate tablets with POS software | time depends on the verision of POS system |  |  | 1 day
Milestone: Staff training for using the tablets
Liaise with vendor to train management |  |  |  | 1 hour
Vendor-led training sessions for managers |  |  |  | 2 hours
Schedule staff meeting to discuss the introduction of the tablets at the restaurants |  |  |  | 2 hours
Other staff training prep |  |  |  | 1 week
Staff (FOH and BOH) training |  |  |  | 4 hours
Milestone: Change Management
Liaise with GM to implement any change that could affect waitstaff tips |  |  |  | 2 hours
Milestone: Tablet project launch
Create a Launch Day plan (staffing, troubleshooting, etc) |  |  |  | 6 hours
Organise tablets' test run with family and friends one day before the launch |  |  |  | 5 hours
Evaluate the test run |  |  |  | 10 hours

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Choosing a tablet vendor
Research tablet system options |  | 2 days | 1 day | 3 days | 1 week | M
Generate quotes and review costs |  | 2 days | 1 day | 2 days | 3 days | M
Test out tablet systems capabilities |  | 5 days | 3 days | 1 week | 10 days | M
Choose a tablet system |  | 2 days | 1 day | 2 days | 3 days | M
Sign contract with menu tablet vendor |  | 2 days | 1 day | 2 days | 5 days | M
Milestone: Tablet delivery
Decide how many tablets are required |  | 4 hours | 3 hours | 5 hours | 1 day | H
Put the order with the vendor |  | 3 hours | 1 hour | 2 hours | 5 hours | H
Old tablets shipment |  | 11 days | 10 days | 11 days | 14 days | H
New tablets shipment |  | 4 weeks | 3 weeks | 4 weeks | 6 weeks | M
Milestone: Tablet installation
Determine the extent of installation at each location in the bar area |  | 5 hours | 1 hour | 3 hours | 1 day | M
Schedule an electrician to wire up the tables |  | 3 hours | 2 hours | 5 hours | 1 day | M
Install tablets in the bar areas at the Downtown and North restaurant locations | - we can’t close the restaurants for a full day we need to schedule two half-days at each location - Notify GMs when their locations need to close for wiring | 4 days | 16 hours | 4 days | 6 days | M
Milestone: creating the tablet visual content
Choose menu items and coupon values to feature in the tablets |  | 1 week | 2 days | 7 days | 2 weeks | L
Send the content to the designers |  | 2 hours | 1 hour | 3 hours | 6 hours | M
Designing of the mock-ups |  | 4 days | 1 day | 2 days | 1 week | M
Evaluate the designs |  | 2 hours | 1 hour | 2 hours | 3 hours | M
Load the mock-ups on the tablets |  | 4 hours | 2 hours | 3 hours | 7 hours | H
Milestone: Tablet integration with existing systems
Establish security measures for data traffic on tablets |  | 1 day | 5 hours | 1 day | 3 days | L
Integrate tablets with POS software | time depends on the verision of POS system | 1 day | 3 hours | 1 day | 3 days | L
Milestone: Staff training for using the tablets
Liaise with vendor to train management |  | 1 hour | 1 hour | 2 hours | 3 hours | H
Vendor-led training sessions for managers |  | 2 hours | 1 hour | 2 hours | 5 hours | H
Schedule staff meeting to discuss the introduction of the tablets at the restaurants |  | 2 hours | 1 hour | 2 hours | 5 hours | H
Other staff training prep |  | 1 week | 3 days | 1 week | 2 weeks | M
Staff (FOH and BOH) training |  | 4 hours | 3 hours | 4 hours | 2 days | M
Milestone: Change Management
Liaise with GM to implement any change that could affect waitstaff tips |  | 2 hours | 1 hour | 2 hours | 3 hours | H
Milestone: Tablet project launch
Create a Launch Day plan (staffing, troubleshooting, etc) |  | 6 hours | 3 hours | 5 hours | 1 day | M
Organise tablets' test run with family and friends one day before the launch |  | 5 hours | 2 hours | 5 hours | 1 day | M
Evaluate the test run |  | 10 hours | 3 hours | 10 hours | 1 day | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Retail and Restaurant Tablet POS: Everything You Need to Know | https://www.nccusa.com/retail-and-restaurant-tablet-pos-everything-you-need-to-know/ | 2022-01-02
How to Develop a Successful POS System Implementation Plan | https://www.talech.com/blog/2020/05/07/resources-how-to-develop-a-successful-pos-system-implementation-plan/ | 2022-01-02

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Commitment to customer satisfaction | Decrease of average table turn time by 30 minutes | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | FALSE
| Decrease of average ticket time for appetizers to 8 minutes |  |  | FALSE
| Decrease of average ticket time for entrees to 12-15 minutes |  |  | FALSE
| Average time of 10 minutes or less in the lobby before guests are seated |  |  | FALSE
| Quicker check-out process (average 1 minute or less) |  |  | FALSE
| 98% of order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order
| Check-out process seamless and easy to navigate for the user | Do all tablets work as expected? | Waitstaff can log into their tablet accounts on the first try
| < 5% of customers/week to report tablets' technical issues | How quickly are customers learning to navigate the tablets? | Tablet error logs report a maximum of one error per shift | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Decrease of average table turn time by 30 minutes | Are customers having a better dining experience with the tablets? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | On a scale of 1-5, 1 being needs improvement and 5 being excellent, how would you rate your overall experience?” | Scaled | 1 | 2 | 3 | 4 | 5
Decrease of average ticket time for appetizers to 8 minutes |  |  | If you ordered appetizers, how long did it take to receive them? | Scaled | less than 7 minutes | between 7 and 10 minutes | more than 10 minutes
Decrease of average ticket time for entrees to 12-15 minutes |  |  | If you ordered entrees, how long did it take to receive them? | Scaled | less than 10 minutes | between 10 and 15 minutes | more than 15 minutes
Average time of 10 minutes or less in the lobby before guests are seated |  |  | Was the waiting in the lobby no longer than 10 minutes? | Yes/No | yes | no
Quicker check-out process (average 1 minute or less) |  |  | Was the check-out process no longer than one minute? | Yes/No | yes | no
98% of order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | The order you received was correct | True/False | TRUE | FALSE
Check-out process seamless and easy to navigate for the user | Do all tablets work as expected? | Waitstaff can log into their tablet accounts on the first try | If you did not find the checkout process easy to use, what were the barriers you encountered? (Select all that apply) | Multiple choice | It was not clear how to access the check-out section on the tablet | The check-out section was slow to load | The check out section did not seem safe enough | I prefer to interact with a person to pay my bill | Other (Please write)
< 5% of customers/week to report tablets' technical issues | How quickly are customers learning to navigate the tablets? | Tablet error logs report a maximum of one error per shift | Did you encounter any issue when using the tablet? | Yes/No | yes | no